Minutes of video conference on Skype.

Present: Sølvi Anvik (Norway), Diana Popa (Romania) and Ingrid Tanner (Norway)

Date: 08.11.11

Time: 12:00 – 13:30

Agenda:

- Check if ICT conclusion is finished.

- Discuss points 13, 15 and 26 on project description. Results finished?

- The final exhibition. When, where, for whom?

- Web site and communication activity.

- Make web quest for next meeting?

- Homework suggestions.

- Other issues? The brochure. E-diary. Suggestions for program in Romania.

- Make appointment for next video conference.

- ICT conclusion is finished.

- Point 13: Analysis of classroom management and role of teacher + SWOT analysis also finished. Point 15: Writing report on management of participating countries finished. Videoconference is held. Point 26: The order of the last 2 meetings in Germany and Romania is switched round. Romania in February with theme: CLIL. Germany in April with the addressing of multiple intelligences.

- The final exhibition (point 28). Of the whole project as far as we’ve got by then: At the final meeting in Germany we will exhibit all our results so far. In each individual institution in May/June: Exhibit and present the results of the project to colleagues, management, press, school web site.

- At meeting in Romania we will go through and update the project web site. All participants bring their products (contribution to the products) to give to Tibor for web site.

- We decided to skip the homework suggestion for the best web quest as we have already dealt with it in Bratislava.

- We also decided to drop the listening task we agreed on in Spain. It is not necessary and we are short of time. New homework will be:

  - Written report on cross-curricular approaches to teaching and learning (point 19)

  - Short presentation of CLIL implementation in the participating institutions. Maximum 10 minutes.

- Brochure – what it should contain?  The brochure should consist of all ideas for good teaching methods that have been treated throughout the project period. The brochure will also function as proof of the work we have been doing. E – diary: Documentation / Log on all activities in each country. Necessary for the final report. Web, e-mails, minutes of meetings, phone calls, all informal activity too. Keep all mails: proof of communication. Remember to inform all participants of this. Should be written in English. Program in Romania: Updating the web page. Go through final report. CLIL presentations. Group work on products. Meetings with only coordinators.

- Next video conference: Tuesday Nov 22nd 2011 at 12:00 Norwegian time. (Romanian time 13:00)